## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP --> | Lines of code | File / Class / Method count | Cyclomatic complexity | Test Coverage | # of test cases | test pass rate | Security findings (SAST) | Code review turnaround | Stories planned vs completed | Defect rate (defects/KLOC) | Defect density per module | Defect resolution time | Person-hours actual vs estimated
0 | 05/04-05/-14 | Team met 2 times to discuss project deliverables and plan; Assigned roles and iter. 0 tasks; Completed iteration 0 documentation (SPPP, risk management plan, progress report, meeting minutes, presentation); Created user stories and imported them into jira; Configured git and set up repo; Proposed, researched, and reviewed system architecture | None | - Making sure documents meet course requirements - Team disagreeing on backend choice for Ai work - Teammates unfamiliar wiht different areas of the tech stack | - Team lead adresses areas that do not meet documentation standards - Team will meet to discuss which options are best for AI functionality - Team members will research the areas that they are unfamiliar with | N/A | N/A | N/A | N/A | N/A | 63.5 | 53.5 | 2.5 | 5 | 22 | 2.5 |  |  | 13.5 | 1.5 | 4 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1
2
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Shaima | 2026-05-11 |  | SPPP sections 1-3 and 4.a |  |  | Used AI to be able to communicate design ideas and vision clearly and professionally.
Kai | 2026-05-11 | ChatGPT | SPPP section 5 | Accepted, slight modification | Modification was adjusting the recommended branching strategy to match our team's decision | Prompt summary: Based on a 4 person team for a six week project, what are the ideal git branching strategies Output summary: Github flow, Gitflow, Trunk-based
Fatimah | 2026-05-11 |  | SPPP section 6 |  |  | AI assisted with metric definitions and PR checklist structure, metrics and tests adapted to the project , checklist reviewed and refined.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Jira | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Kai Fernandes | Configuration management plan, Risk management plan, general restructuring of SPPP (deleting directions, normalizing format) |  |  |  | Iteration 0 slides and presentation |  |  |  | Making agenda for meetings and keeping team on track, as well as keeping minutes; Ensuring documentation is consistent and up to course standards

## studentName (hidden)
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Shaima Nimeri
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/09-05/13 | 37.5 | 35 | 2.5 | 0 - learn jira used AI for that 1 - make project plan, setup zoom meeting 2 - designed user stories 5- spoke to potential app users to get an idea about expectations and problems | 0 | 20 | 10 | 0 | 0 | 5 | 0 | 0 | Used Claud to make user stories understandable for better communiction and create document for team github usage | 1. Wrote sections 1-3 and section 4 a-c in SPPP 2. Created user stories 3.Attended 2 meetings to discuss plans for project success | making sure all requirements are met and no documents are missed | check with my group in zoom meeting | 3-implementation 4 communtion/ managment 4 test | 25

## Fatimah Hassan
Your Lead Roles: Security lead and Configuration Co-lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10 - 05/14 | 9.5 | 7 | 2.5 | 0 - Watched intro RAG videos, read LangChain.js docs, started AI/LLM learning plan 1 - Participated in team brainstorm on project idea; contributed Patient Pathway AI proposal combining workflow + RAG 2 - Reviewed proposed system architecture (React + Express + LangChain.js + ChromaDB + PostgreSQL) 5 - Posted class introduction on Discord; coordinated with team on Discord; discussed scope boundary 6 - Lab 1: configured Git, cloned team repo, created lab1 branch, edited team.md, pushed PR 7 - Drafted Section 6 (Quality Assurance Plan) of the SPPP | 2 | 1 | 0.5 |  |  | 2 | 1.5 | 3 | Used Claude to: (1) brainstorm and stress-test project topic options, (3) explain LangChain.js trade-offs vs Python for our backend choice, (4) draft Section 6 (QA Plan) structure and exam-prep companion. Verified all suggestions, adjusted to my voice and team context. Useful for accelerating drafting; verification still required for accuracy and team fit. | 1. Lab 1 completed: lab1 branch pushed with team.md introduction. 2. Project topic proposal contributed (Patient Pathway AI: workflow + RAG); accepted by team. 3. Section 6 (QA Plan) drafted for the SPPP, including metrics, coding standards, code review checklist, testing strategy, defect management. 4. Volunteered for Security Lead role with Configuration Co-Lead support. | 1. Backend choice (Express + LangChain.js) is less mature than Python for AI work --- tutorial coverage and ecosystem are weaker; risk of friction during RAG implementation. 2. Team is still waiting on confirmation of one teammate (Jianing); role assignments not finalized. 3. New to RAG, embeddings, and vector databases — learning curve ahead of Iteration 1. | 1. Risk documented in SPPP Section 4.b. Fallback plan: pivot to Express + small Python AI microservice (Option B) if LangChain.js friction appears in Iter 1 Week 1. 2. Executing structured 4-week AI learning plan: DeepLearning.AI LangChain course, RAG tutorial, hands-on PDF Q&A build before Iter 1 starts. | 0 - Continue LangChain.js + RAG learning (DeepLearning.AI course, PDF chat tutorial) 2 - Help finalize architecture diagram and threat model for FR-1 (login) 5 - Attend team meeting; help finalize SPPP and submit Iteration 0 release 6 - As Configuration Co-Lead: set up branch protection, basic GitHub Actions CI workflow, .gitignore, PR template 6 - As Security Lead: add npm-audit + CodeQL workflow to CI 7 - Final review of SPPP before submission | ~12

## Kolya Gavlishin
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 5/05-5/14 | 4.5 | 2 | 2.5 | 0 - research testing and QA strategies 1 - work with team on project requirements 2 - work with team on project design 7 - prepare and present interation 0 | 2 | 1 | 1 |  |  |  |  | 1 | No significant AI use this week | 1. Reviewed SPPP contributions of other members and gave my feedback during the meeting 2. Met with Kai to plan out and record the presentation 3. Set up git and pushed to team's repo 4. Volunteered for QA Lead and Design and Implementation Co-Lead | 1. Not familiar with QA and testing strategies | 1. I researched various testing strategies and reviewed the SPPP to familiarize myself with them | 0 - continue to research testing strategies and processes

## Kai Fernandes
Your Lead Roles: Team lead, Configuration Co-lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/05 - 05/14 | 12 | 9.5 | 2.5 | 0 - relearning git and jira 5 - Organizing team meeting, document management, risk management sheet, SPPP, recorded and created presentation, submitted documentation 6 - Lab 1: configured Git, edited team.md, created PR for lab1 | 1 |  |  |  |  | 8.5 |  |  | ChatGPT - helped troubleshoot git commands and finding files, used the command given to reset a branch | Wrote configuration management section of SPPP and completed risk management sheet and summary for SPPP, restructured SPPP to have consistent formatting and follow instructions (added titles for requirements and made sure they were in the story format), managed progress report, worked with Kolya to create and present interation 0 presentation | Unfamiliar with react | Learn react basics through independent research | Continue learning necessary tools from the tech stack, lead documentation and task delegation, complete user stories | ~13