## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP --> | Lines of code | File / Class / Method count | Cyclomatic complexity | Test Coverage | # of test cases | test pass rate | Security findings (SAST) | Code review turnaround | Stories planned vs completed | Defect rate (defects/KLOC) | Defect density per module | Defect resolution time | Person-hours actual vs estimated
0 | 05/04-05/14 | Team met 2 times to discuss project deliverables and plan; Assigned roles and iter. 0 tasks; Completed iteration 0 documentation (SPPP, risk management plan, progress report, meeting minutes, presentation); Created user stories and imported them into jira; Configured git and set up repo; Proposed, researched, and reviewed system architecture | None | - Making sure documents meet course requirements - Team disagreeing on backend choice for Ai work - Teammates unfamiliar wiht different areas of the tech stack | - Team lead adresses areas that do not meet documentation standards - Team will meet to discuss which options are best for AI functionality - Team members will research the areas that they are unfamiliar with | N/A | N/A | N/A | N/A | N/A | 63.5 | 53.5 | 2.5 | 5 | 22 | 2.5 |  |  | 13.5 | 1.5 | 4 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1 | 05/15-5/25 | Got intial application running including frontend, backend, and database; Users can log in/ log out securely; Patients can register, calculate BMI, pick a specialist, and new their next steps in the process; Coordinators can view and search for patients, update patient statuses, and assign adn track specialist recommendations; Completes 17 user story points (9 stories) | - Github branch mixups - Firebase on Fatimah private email - Created non protected routes that should hav ebeen protected | - Teammates unfamiliar with specific tools in the tech stack - API port mismatch | - team members research areas they are unfamiliar with - find long term solution for firebase acces - corrected ports in VITE_API_URL - team will be more vigilant with checking branches before commits/PRs - team will be sure to create protected routes moving forward | 17 | 0 | 5 | 0 |  | 100 | 90.5 | 3 | 4.5 | 3 | 15 | 52 | 7.5 | 10.5 | 8.5 | 5 |  | 14968 | 52 | ~3.5 per function | 80% | 62 | 87.1% | N/A (SAST planned for Iteration 2) | ~ 2 days | Planned: 9 Completed: 9 | 0.334 defects/KLOC | Auth: 1 Infrastructure: 1 Patient routes: 0 Audit log: 0 Secrets: 0 Frontend: 0 | 1.8 days | Actual: 90.5 Estimated: 55-70
2
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Week 1
Shaima | 2026-05-11 |  | SPPP sections 1-3 and 4.a |  |  | Used AI to be able to communicate design ideas and vision clearly and professionally.
Kai | 2026-05-11 | ChatGPT | SPPP section 5 | Accepted, slight modification | Modification was adjusting the recommended branching strategy to match our team's decision | Prompt summary: Based on a 4 person team for a six week project, what are the ideal git branching strategies Output summary: Github flow, Gitflow, Trunk-based
Fatimah | 2026-05-11 | Claude ¦ ChatGPT | SPPP Section 6 – Quality Assurance Plan, quality metrics definition, PR review checklist, testing strategy, CI/CD quality considerations, and defect tracking approach. |  | AI-generated suggestions were reviewed and refined to align with the project scope, healthcare workflow requirements, and the team’s selected Agile process. Quality metrics, pull request checklist items, and testing approaches were adjusted to better fit the BariatricPath system architecture and team workflow. Some generated recommendations were simplified to match the iteration scope and available development timeline. | Used AI to assist in drafting the Quality Assurance Plan, including defining software quality metrics, testing strategies, review processes, defect management workflow, and pull request checklist structure. AI also helped generate examples of unit testing, integration testing, and CI/CD quality practices relevant to a healthcare-oriented AI-assisted application. Outputs were evaluated, selectively adopted, and revised to ensure consistency with the team’s architecture, project scope, and Agile iteration goals.
Week 2/3 (Iteration 2)
Fatimah | 2026-05-18 | Claude ¦ ChatGPT | Implementation of BARI-7 (registration) and BARI-9 (logout) -- auth routes, middleware, React auth pages | Accepted, with modification | All generated code reviewed line by line, adapted to our Prisma schema and Firebase architecture, and tested manually before committing. Skipped suggested packages (jsonwebtoken, bcryptjs) that didn't fit our Firebase-based design. | Prompt summary: how to implement Firebase + Express authentication with role-based access. Output: register/login/me endpoints, verifyAuth/requireRole middleware, auth UI components
Kolya | 5/15-5/22 | Claude Code | Implementation of Coordinator Dashboard: Patient Table Search by DOB, Name, and MRN Filters by Insurance, Status, and Specialist Unit and Integration Test Creation Help with debugging issues with fetching and authentication | Accepted with Modification and Refactoring | I evaluated all the generated code line by line to understand it and make sure it made sense for the project and the specific features that I was working on. It was not that helpful for debugging issues with authentication. I had to rely on my teammates for that. It was very helpful for implementation of the user stories, desired features, and tests. | AI Generated Summary of My AI Log: AI Log Summary Tool used throughout: Claude Code (claude-sonnet-4-6) All sessions dated: 2026-05-24 Session 1 — Documentation & Schema (3 prompts) Your prompts: You asked AI to proofread and expand your database schema description, then generate a UML diagram, then review and expand your UI description of the coordinator dashboard. AI contributions: Caught factual errors in your schema description (wrong entity count, wrong data type for isRead) and filled in missing details about Firebase auth, enum types, cascade behavior, and default values. Generated a complete Mermaid UML class diagram saved to docs/Iteration0/personal docs/schema-uml.md. Expanded the dashboard UI description with precise color thresholds, debounce timing (300ms), loading/error/empty states, and specialist badge color semantics. Session 2 — Feature Build: Patient List (13 prompts) This was the main development session. You drove step-by-step with tightly scoped prompts: Prompt Your ask AI's code contribution 1 Fix seed data to match insurance/specialist/checklist rules Rewrote seed.js with correct BMI-based specialist types, varied insurance statuses, and per-type checklist values 2 Update GET /api/patients to return progress + support filters Added computeProgress() to searchDB.js, wired filter params to the Prisma query, updated patients.js route 3 Build PatientTableList.jsx with all columns; extract from dashboard; add filter dropdowns Created ProgressBar.jsx, PatientTableList.jsx; updated CoordinatorDashboard.jsx 4 Extract filter dropdowns into their own components Created SpecialistFilter.jsx and InsuranceFilter.jsx 5 Move progress logic to calculateProgress.js Created calculateProgress.js, updated imports across searchDB.js and patients.js 6 Move date validation logic to validateDate.js Created validateDate.js, updated searchDB.js imports 7 Write Jest unit tests for calculateProgress.js Created 25 tests across 6 groups covering standard and edge cases — all passed 8 "What's the test command?" npx jest calculateProgress.test.js 9 Date search is broken Found 2 bugs: circular self-require in validateDate.js and a UTC/local timezone mismatch in getDateRange(); fixed both 10 Move search/fetch logic into SearchBar.jsx Created SearchBar.jsx owning all state/fetch/debounce; simplified CoordinatorDashboard.jsx to just layout 11 Fix row height inconsistency; fix progress bar colors Fixed N/A row height in ProgressBar.jsx; changed green threshold to 100% only 12 Write integration tests for the patient list endpoint Created 16 integration tests in routes/patients.test.js using supertest + mocked Prisma — all passed 13 Transfer session to AI Log.txt Transcribed all prompts/outputs to the log file Session 3 — Bug Fix: API Connectivity (5 prompts) Your prompts: You reported a JSON parse error in the browser (no data coming back from the API) and then CORS errors. You also asked about alternative approaches and chose the env var approach over the Vite proxy. AI contributions: Diagnosed the JSON parse error as a missing Vite proxy config (Vite was returning HTML instead of API data). Added the proxy to vite.config.js, then identified a second bug: wrong port (5000 vs. 5001). Diagnosed the CORS error as api.js bypassing the proxy with absolute URLs. When you chose the env var approach instead, removed the proxy and updated SearchBar.jsx to use import.meta.env.VITE_API_URL for its fetch call. Overall pattern: You used AI as a pair programmer with tight, incremental prompts — each scoped to one file or concern. AI's main contributions were new files (calculateProgress.js, validateDate.js, SearchBar.jsx, PatientTableList.jsx, ProgressBar.jsx, filter components, test files), bug diagnosis, and documentation expansion. You reviewed each output before moving to the next step.
Kai | 05/15-05/24 | Claude ¦ ChatGPT | Implementation of BMI calculation and eligibility, Infrastructure testing, unit testing, creating github workflow for metric tracking, Class diagram review, routing confirmation, debugging | Accepting with modification and validation | I evaluated all lines of code and the code structure, making sure it was readable and correct, also testing the code often to make sure there were no hidden bugs | STD/Infrastructure testing- Prompt summary: I am in charge of infrastructure smoke tests. Provide full step by step instructions on how to do the necessary tests, what tools i should use, files i have to make, etc as someone that is new to testing. (I also provided the table format that my team is using for manual testing in our STD) SDD introduction - https://claude.ai/chat/f6a09ede-4e2a-4b38-959b-7af92f126e7a SDD section 7 - Prompt summary section 7: Given the following classes and general structure, draft some descriptions and any missing class connections Output summary: Gave many good suggestions on missing connections and gave description of each class BMI input validation- Prompt summary: I asked for basic input validation to be added to my code such as NaN values, boundaries to add (no zeroes), etc Output summary: Provided a lightly modified React component that prevents invalid BMI calculations and blocks bad inputs before navigation. BMI boundary testing - Prompt summary: I listed existing BMI tests and asked for feedback. Output summary: Confirmed the coverage was solid and explained that the tests already handle calculation accuracy, edge cases, rounding, and input parsing appropriately. Routing logic - Prompt summary: I shared routing logic that redirects users based on BMI and asked about correctness. Output summary: Reviewed the React Router conditional navigation and confirmed it was correct, including state passing and formatted BMI handling. Github workflow - Prompt summary: I asked how to set up a GitHub Actions workflow to track metrics like lines of code (LOC), file/class counts, cyclomatic complexity, and test coverage. I also needed help installing tools like cloc in CI and fixing issues where the workflow was failing, not showing duration, or not updating after I pushed new commits. Output summary: Explained how to structure a GitHub Actions workflow to collect and report metrics in CI. Guided me through using cloc for LOC, ESLint for complexity/static analysis, and CI logs or PR comments for output reporting. Also helped troubleshoot GitHub Actions issues like failed runs, missing refresh after commits, and how workflow triggers and re-runs actually work.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Jira | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Kai Fernandes | Configuration management plan, Risk management plan, general restructuring of SPPP (deleting directions, normalizing format) |  | Wrote Class Diagrams section and introduction | Infrastrusture testing section in Manual testing | Iteration 0 slides and presentation |  | Manual infrastructure smoke tests and unit testing with jest for bmi calculation and bmi ineligible pages |  | Making agenda for meetings and keeping team on track, as well as keeping minutes; Ensuring documentation is consistent and up to course standards
Kolya Gavlishin |  |  | 2. SDD: Wrote Database section and part of the UI section | 3. STD: Added to document testing implemented on my feature branch | Iteration 0 slides and presentation | 1. Project code: Coordinator dashboard that displays patient data. Features search by name, DOB, and MRN along with filters by insruance status and specialist type | Unit tests for Coordinator search, date validation, and to compute patient progress, and integration test for /patients route. Manueal testing of Coordinator Dashboard functionality.

## studentName (hidden)
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Shaima Nimeri
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/09-05/13 | 37.5 | 35 | 2.5 | 0 - learn jira used AI for that 1 - make project plan, setup zoom meeting 2 - designed user stories 5- spoke to potential app users to get an idea about expectations and problems | 0 | 20 | 10 | 0 | 0 | 5 | 0 | 0 | Used Claud to make user stories understandable for better communiction and create document for team github usage | 1. Wrote sections 1-3 and section 4 a-c in SPPP 2. Created user stories 3.Attended 2 meetings to discuss plans for project success | making sure all requirements are met and no documents are missed | check with my group in zoom meeting | 3-implementation 4 communtion/ managment 4 test | 25
2026-02-03 | 05/13-05/25 | 50 | 49 | 3 | 2- designed the project structure and added the code to github main branch for team inital pull 2- designed the schema fo the project 5-created and added all users stories to Jira and created 3 sprints with deadlines and started sprint1 according to specifed dates and guided the team member through the process of selecting their stories 5-created database on Supabase and added team members 4-performed 7 PR reviews including running the code provided for testing and submitting feed back with fixes 6- updated .env for client, server and docker files and shared structure with team members fixed confuration of Docker-compose.yml to connect to database and fixed issues in code to make sure .env get used 3- fixed BARI-11 and BARI13 bmi calculator and not eligable page 3- added dateofbirth to registration page 1-PR reviews where made to satify project requriments and securtiy requirements 2-provided project logo 5-was responsive in Discord to team question and requests 3- performed merges to dev and reviewing code 3- performed code intergation from different user stories |  |  | 10 | 35 hours |  | 5 hours | 2 hrs |  |  | 1. created project structure on main branch on github 2. designed project schema and updated it 3.created jira board and user stories in 3 sprints with deadlines 4.Created project supabase.com and added the team members 5.Did the PR reviews to all user stories with recommended fixes and changed the for user stories BARI-11 and BARI13 do to time crunch 6.Fixed configurations in Docker-compose.yml file 7. Added dateofbirth to registration page to address patient registraion 8.Added table relation between user and patient table for patient table to update registered patient 9. After giving PR review and recieving updated code fixed any issues not addressed or new to be able to meet deadline For BARI-12 specialist recommendation added verifyAuth middleware on POST/recommendaiton and PATCH/:id/specialist and added Navbar to thankyou page 7. performed integration to all user stories 8. Updated SPPP document with required changes assigned to me 9.Updated STP docoment REST API section 10 integration details:1. PR #9 from ijnkyle Specialist recommendation logic: BMI form with routing that recommends a specialist based on BMI value and surgery history. Fixed issues including missing auth middleware, hardcoded patient ID, and shared Prisma instance. 2. PR #10 form lijnkyle : Thank You confirmation page shown after patient submits their information. Fixed missing Navbar on loading and error states. 4. PR #12 from Fatimah: Express app split into app.js and index.js for testability; auth route tests added with Jest and Supertest. Updated tests to match current schema (dateOfBirth, Patient mock, patientId assertions). 4. PR #13 from Kolya : Patient search by name, MRN, and date of birth with specialist type and insurance filters; integrated into Coordinator Dashboard. Fixed Prisma mock to use shared instance. 5.PR #14 from Kai: BMI calculation and eligibility. This PR was not up to date with dev and could not be merged as-is. The code was pulled in and the following fixes were applied: - Fixed BMI eligibility threshold from > 27 to >= 27 - Replaced inline BMI formula with the shared calculateBMI() utility from bmi.js - Added weight validation to calculateBMI() - Replaced alert() with showError() toast for input validation - Replaced location.state user dependency with useAuth() from AuthContext - Replaced bare inputs with Bootstrap form-control classes - Fixed broken catch block indentation in Register.jsx - Cleaned up unused imports and dead styles in BmiIneligiblePage - Added BMI result display on the calculation page before navigating - Added BMI persistence to the database on continue Additional fixes: 1. Patient registration now collects date of birth and automatically creates and links a Patient record with an auto-generated MRN 2. BMI result displayed on calculation page before navigating; BMI saved to the database 3.Email lookup fixed for patient submit notification 5.Prisma upgraded to v6 for Node.js v24 compatibility 6.Bariatric Pathway logo added to navbar An intergration branch was create to include all implemented fixed stories feature/Shaima-integration and PR was created and assigned to Fatima to respond to merge to dev All PR reviews were manually testing by running server and client Recored iteration 1 demo and participated in presentation |  | set meeting time to start iteration 2

## Jianing Li
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week

## Fatimah Hassan
Your Lead Roles: Security lead and Configuration Co-lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10 - 05/14 | 9.5 | 7 | 2.5 | 0 - Watched intro RAG videos, read LangChain.js docs, started AI/LLM learning plan 1 - Participated in team brainstorm on project idea; contributed Patient Pathway AI proposal combining workflow + RAG 2 - Reviewed proposed system architecture (React + Express + LangChain.js + ChromaDB + PostgreSQL) 5 - Posted class introduction on Discord; coordinated with team on Discord; discussed scope boundary 6 - Lab 1: configured Git, cloned team repo, created lab1 branch, edited team.md, pushed PR 7 - Drafted Section 6 (Quality Assurance Plan) of the SPPP | 2 | 1 | 0.5 |  |  | 2 | 1.5 | 3 | Used Claude to: (1) brainstorm and stress-test project topic options, (3) explain LangChain.js trade-offs vs Python for our backend choice, (4) draft Section 6 (QA Plan) structure and exam-prep companion. Verified all suggestions, adjusted to my voice and team context. Useful for accelerating drafting; verification still required for accuracy and team fit. | 1. Lab 1 completed: lab1 branch pushed with team.md introduction. 2. Project topic proposal contributed (Patient Pathway AI: workflow + RAG); accepted by team. 3. Section 6 (QA Plan) drafted for the SPPP, including metrics, coding standards, code review checklist, testing strategy, defect management. 4. Volunteered for Security Lead role with Configuration Co-Lead support. | 1. Backend choice (Express + LangChain.js) is less mature than Python for AI work --- tutorial coverage and ecosystem are weaker; risk of friction during RAG implementation. 2. Team is still waiting on confirmation of one teammate (Jianing); role assignments not finalized. 3. New to RAG, embeddings, and vector databases — learning curve ahead of Iteration 1. | 1. Risk documented in SPPP Section 4.b. Fallback plan: pivot to Express + small Python AI microservice (Option B) if LangChain.js friction appears in Iter 1 Week 1. 2. Executing structured 4-week AI learning plan: DeepLearning.AI LangChain course, RAG tutorial, hands-on PDF Q&A build before Iter 1 starts. | 0 - Continue LangChain.js + RAG learning (DeepLearning.AI course, PDF chat tutorial) 2 - Help finalize architecture diagram and threat model for FR-1 (login) 5 - Attend team meeting; help finalize SPPP and submit Iteration 0 release 6 - As Configuration Co-Lead: set up branch protection, basic GitHub Actions CI workflow, .gitignore, PR template 6 - As Security Lead: add npm-audit + CodeQL workflow to CI 7 - Final review of SPPP before submission | ~12
WEEK 2
2 | 05/15 - 05/19 | ~ 14 | ~12 | 2.5 | 0 - Continued LangChain/RAG learning; researched Firebase + JWT integration patterns
1 - Reviewed Lab 2 requirements; refined Authentication user stories (INVEST + acceptance tests)
2 - Designed the auth architecture (Firebase Auth + Express token verification); created entity class diagram
[5 empty] | 3 - Implemented BARI-7 (patient registration) and BARI-9 (logout): register/login/me endpoints, verifyAuth + requireRole middleware, RegisterPage, LoginPage, Navbar, AuthContext, ProtectedRoute | 1.5 | 1 | 1.5 | 5 | 1.5 | 1 | 1.5 | 1 | Used Claude tand ChatGpt o: troubleshoot the Prisma schema error (invalid "Enum" type), | 1. Implemented BARI-7 (patient registration) and BARI-9 (logout) — register, | 1. schema.prisma on dev had invalid "Enum" types — blocked prisma generate for | 1. Fixed the schema back to "String"; flagged to the team in Discord; included | 1- Address PR review feedback from Shaima; help integrate auth into protected routes | 13
[5 empty] | 4 - Functional testing of the auth flow (registration, login, logout, role redirect, session persistence) | [8 empty] | debug the API port mismatch (5001 vs 3000), structure the Firebase + Express | login, /me endpoints with Firebase token verification, plus verifyAuth and | the whole team until corrected to "String". | the fix in my PR. Suggested adding a CI step that runs prisma generate so a | 2 - Write Jest + Supertest unit/integration tests for the auth endpoint
[5 empty] | 5 - Coordinated with team on Discord; shared Firebase credentials; discussed schema fix | [8 empty] | auth implementation, design the verifyAuth/requireRole middleware, and review | requireRole middleware for protected routes. | 2. API port mismatch (frontend calling 5001, backend on 3000) caused /auth/me | broken schema can't reach dev again. | 3 - As Config Co-Lead: set up GitHub Actions CI (lint, test, prisma generate, npm audit
[5 empty] | 6 - Configured .gitignore/.dockerignore; created server & client Dockerfiles and docker-compose.yml; set up local PostgreSQL | [8 empty] | the auth UI. Also used it to clarify which npm packages were actually needed | 2. Built the auth frontend: RegisterPage, LoginPage, Navbar, AuthContext, | to 404 and bounced users back to login. | 2. Corrected VITE_API_URL to port 3000 and restarted Vite — resolved. | 4 - As Security Lead: add CodeQL workflow; document STRIDE threat model for login
[5 empty] | 7 - Worked on Lab 2 document; created Jira user stories | [8 empty] | (skipped jsonwebtoken/bcryptjs since Firebase handles those). All code was | ProtectedRoute, with Google sign-in and role-based redirect. | 3. Firebase project is under my personal Google account — team needs a | 3. Shared Firebase credentials via the team Drive; offered Console access to | 5 - Iteration 1 demo prep and team coordination
[14 empty] | reviewed line by line, tested manually, and adapted to our Prisma schema and | 3. Fixed a build-breaking schema error (invalid "Enum" type) blocking the team. | long-term plan for shared ownership. | teammates. Will revisit shared ownership before deployment.
[14 empty] | architecture before committing. | 4. Created the project Docker setup (server/client Dockerfiles, docker-compose).
5. Completed Lab 2 user stories in Jira and the Lab 2 document.
6. Opened a PR (feature/fatimah-patient-crud → dev), assigned Shaima as reviewer.

## Kolya Gavlishin
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 5/05-5/14 | 4.5 | 2 | 2.5 | 0 - research testing and QA strategies 1 - work with team on project requirements 2 - work with team on project design 7 - prepare and present interation 0 | 2 | 1 | 1 |  |  |  |  | 1 | No significant AI use this week |  | 1. Not familiar with QA and testing strategies | 1. I researched various testing strategies and reviewed the SPPP to familiarize myself with them | 0 - continue to research testing strategies and processes
2 | 5/15-5/22 | 26 | 23 | 3 | 0 - figuring out starter and skeleton code and file structure 1 - reading through stories, acceptance tests, and sub tasks 2 - figuring out how to best structure code into separate files and modules, contirbuted to UI and Database sections of SDD 3 - creating coordinator dashboard with search funtionality 4 - creating unit and implementation tests, testing functionality manually in browser, trouble shooting bugs with fetching data 5 - attended meetings, minute taker for meeting 4 6 - troubleshooting git issues (rookie mistakes on my end), integrating authentication into my feature branch and adding authentication to routes, 7 - lab2 and quiz | 2 | 2 | 2 | 6 | 2 | 3 | 4 | 3 | I used Claude Code for implementing the functionality of my stories. I provided it context with the user stories, acceptance tests, sub tasks, and which files I wanted it to edit. I re-prompted it when I needed to refactor. For example, when I wanted to modularize some of the code for searching or create separate components for the dashboard. Additionally, it was helpful with creating unit tests and integration tests. I also used to troubleshoot issues and bugs. All the code was reviewed by me to ensure quality, and I tested its functionality manually. | 1. Project code: Coordinator dashboard that displays patient data. Features search by name, DOB, and MRN along with filters by insruance status and specialist type 2. SDD: Wrote Database section and part of the UI section 3. STD: Added to document testing implemented on my feature branch | 1. Git: I was accidentally on the same branch as another team memeber which led to some tangled commits and lost code. This happened very early on, so thankfully I did not lose that much work. 2. Authentication: I had an issue with the authentication functionality after it was merged to dev. 3. Authentication: I did not protect the routes when I submitted my first PR. | 1. I created a new spearate branch that only I was using. I had no more issues with Git after that. 2. I collaborated with my team members to debug. It was discovered that there was a file missing in the dev branch. Once it was added, the authentication worked for me. 3. Shaima pointed out the issue and how to fix it. I implemented those changes and edited the tests to reflect the edits. | Implementing more user stories Editing STD, SDD, and SPPP docs Lab 3 Quiz 2 | 20-25 hours

## Kai Fernandes
Your Lead Roles: Team lead, Configuration Co-lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/05 - 05/14 | 12 | 9.5 | 2.5 | 0 - relearning git and jira 5 - Organizing team meeting, document management, risk management sheet, SPPP, recorded and created presentation, submitted documentation 6 - Lab 1: configured Git, edited team.md, created PR for lab1 | 1 |  |  |  |  | 8.5 |  |  | ChatGPT - helped troubleshoot git commands and finding files, used the command given to reset a branch | Wrote configuration management section of SPPP and completed risk management sheet and summary for SPPP, restructured SPPP to have consistent formatting and follow instructions (added titles for requirements and made sure they were in the story format), managed progress report, worked with Kolya to create and present interation 0 presentation | Unfamiliar with react | Learn react basics through independent research | Continue learning necessary tools from the tech stack, lead documentation and task delegation, start user stories | ~13
2 | 05/15 - 05/19 | 9.5 | 8.5 | 1 | 0 - learning docker (lab 1) and react 1 - creat user stories for icebox (lab 1) 3 - Implement BMI input story 5 - Update SPPP and risk management; Get familiar with SDD; create agendas for team meetings; Coordinate with team through discord 6 - set up docker locally and learn how to run team docker files | 2.5 | 1.5 |  | 1.5 |  | 2 | 1 |  |  | Updated SPPP with team and professor recommendations; Updated risk management; Learned how to run our docker files; Implemented BMIinput user story; guided team through discussions and agenda for meetings; began visual design (wireframes) for team to get cohesive vision of what the pages will look like | Unfamiliar with Docker | Learned Docker through lab and independent research | Review code from teammates, lead documentation and task delegation, finish user stories, put together iteration 1 release on github | ~14
3 | 05/20-05/25 | 19.5 | 16.5 | 2 | 0 - learning supabase/prisma 2 - Wrote Class Diagrams with class descriptions in SDD 3 - work on Bari11 and bari-13 4 - Manual and Automated Unit testing for Bari 11 and 13 and then infrastructure testing for STD 5 - create agendas for team meetings, manage documentation needed for iteration 1 (including final review / updates before submission), touch base with team members to follow up on their responsible sections 6 - managed environment problems locally connecting the database to the backend 7 - Created github workflow to analyze metrics | 1 |  | 1.5 | 6 | 4 | 1.5 | 3 | 1 |  | Update SPPP with current iteration in the timeline; Update Risk management by updating how we handle risks and likelihood/impact for existing risks; Implement intial Bari-11 and Bari-13 code; Write Class Diagrams section in SDD; Started Infrastructure testing for STD; | Unfamiliar with many testing practices ; Had trouble getting the docker environment to run correctly and getting the database to connect for registration and log in; Unfamiliar with github workflows | Learned how to use Jest and Postman ; Debugged using ChatGPT and Claude until problem was understood and fixed; Also learned github workflows and github actions | Delegate tasks for iteration 2; pick user stories, split into smaller tasks, and start implementing; plan for testing more; lab 3; quiz 2 | ~20